## Richard
User stories | Estimation (in hours)
1. Create three search bar (cuisuine type, price level, ETA). Search bars probably act as a form | 2
Having different options for each category that user can select. | 2 |  |  | hour for each category. Max 3 hours
For example for cuisine type there will be options like Thai, Indian etc. | 1
2. Sign up for Yelp Developer Account and get familiar with what API's to use |  | 4
3. Start Making sample API calls | 2
4. Take the user input from user and pass it to the API | 1
5. Retrive the info from API and show it in the display | 1.5
6. Design the output | 2
7. Get the coordinates of the user through google maps | 2
8. Get the coordinates of the restaurents that we receive from API call | 2
9. Then pass these info to Google distance matrix API to calculate the expected arrival time by default show walking
10. Display the result on the screen | 1
11. Sort by different filters |  |  | 1
Total |  |  | 21.5

## Rahaf
User stories | Estimation (in hours)
1. Create three search bar (cuisuine type, price level, ETA). Search bars probably act as a form | 1.5
Having different options for each category that user can select. | 1
For example for cuisine type there will be options like Thai, Indian etc. | 1
2. Sign up for Yelp Developer Account and get familiar with what API's to use |  | 1
3. Start Making sample API calls | 1
4. Take the user input from user and pass it to the API | 3
5. Retrive the info from API and show it in the display | 2
6. Design the output | 2
7. Get the coordinates of the user through google maps | 1
8. Get the coordinates of the restaurents that we receive from API call | 2.5
9. Then pass these info to Google distance matrix API to calculate the expected arrival time by default show walking | 5
10. Display the result on the screen | 1
11. Sort by different filters | 2
Total | 24

## Asif
User stories | Estimation (in hours)
1. Create three search bar (cuisuine type, price level, ETA). Search bars probably act as a form | 1
Having different options for each category that user can select. | 1 |  |  | hour for each category. Max 3 hours
For example for cuisine type there will be options like Thai, Indian etc. | 1
2. Sign up for Yelp Developer Account and get familiar with what API's to use |  | 1
3. Start Making sample API calls | 1
4. Take the user input from user and pass it to the API | 2
5. Retrive the info from API and show it in the display | 2
6. Design the output | 2.5
7. Get the coordinates of the user | 1
8. Get the coordinates of the restaurents that we receive from API call | 2
9. Then pass these info to Google distance matrix API to calculate the expected arrival time by default show walking | 5
10. Display the result on the screen | 1
Total |  |  | 20.5

## Group
User stories | Estimation
1. Create three search bar (cuisuine type, price level, ETA). Search bars probably act as a form | 1.5
Having different options for each category that user can select. | 1.3333
For example for cuisine type there will be options like Thai, Indian etc. | 1
2. Sign up for Yelp Developer Account and get familiar with what API's to use |  | 2
3. Start Making sample API calls | 1.3333
4. Take the user input from user and pass it to the API | 2
5. Retrive the info from API and show it in the display | 1.8333
6. Design the output | 2.1667
7. Get the coordinates of the user through google maps | 1.3333
8. Get the coordinates of the restaurents that we receive from API call | 2.1667
9. Then pass these info to Google distance matrix API to calculate the expected arrival time by default show walking | 3.3333
10. Display the result on the screen | 1
11. Sort by different filters | 0.66667
Total | 21.6667