## Richard
User stories | Estimation (in hours)
1. Create three search bar (cuisuine type, price level, ETA). Search bars probably act as a form
Having different options for each category that user can select. |  |  | hour for each category. Max 3 hours
For example for cuisine type there will be options like Thai, Indian etc.
2. Sign up for Yelp Developer Account and get familiar with what API's to use
3. Start Making sample API calls
4. Take the user input from user and pass it to the API
5. Retrive the info from API and show it in the display
6. Design the output
7. Get the coordinates of the user through google maps
8. Get the coordinates of the restaurents that we receive from API call
9. Then pass these info to Google distance matrix API to calculate the expected arrival time by default show walking
10. Display the result on the screen
11. Sort by different filters
Total |  | 0

## Rahaf
User stories | Estimation (in hours)
1. Create three search bar (cuisuine type, price level, ETA). Search bars probably act as a form | 1.5
Having different options for each category that user can select. | 1
For example for cuisine type there will be options like Thai, Indian etc. | 1
2. Sign up for Yelp Developer Account and get familiar with what API's to use |  | 1
3. Start Making sample API calls | 1
4. Take the user input from user and pass it to the API | 3
5. Retrive the info from API and show it in the display | 2
6. Design the output | 2
7. Get the coordinates of the user through google maps | 1
8. Get the coordinates of the restaurents that we receive from API call | 2.5
9. Then pass these info to Google distance matrix API to calculate the expected arrival time by default show walking | 5
10. Display the result on the screen | 1
11. Sort by different filters | 2
Total | 24

## Asif
User stories | Estimation (in hours)
1. Create three search bar (cuisuine type, price level, ETA). Search bars probably act as a form | 1
Having different options for each category that user can select. | 1 |  |  | hour for each category. Max 3 hours
For example for cuisine type there will be options like Thai, Indian etc. | 1
2. Sign up for Yelp Developer Account and get familiar with what API's to use |  | 1
3. Start Making sample API calls | 1
4. Take the user input from user and pass it to the API | 2
5. Retrive the info from API and show it in the display | 2
6. Design the output | 2.5
7. Get the coordinates of the user | 1
8. Get the coordinates of the restaurents that we receive from API call | 2
9. Then pass these info to Google distance matrix API to calculate the expected arrival time by default show walking | 5
10. Display the result on the screen | 1
Total |  |  | 20.5

## Group
User stories | Estimation
1. Create three search bar (cuisuine type, price level, ETA). Search bars probably act as a form | 0.83333
Having different options for each category that user can select. | 0.66667
For example for cuisine type there will be options like Thai, Indian etc. | 0.66667
2. Sign up for Yelp Developer Account and get familiar with what API's to use |  | 0.66667
3. Start Making sample API calls | 0.66667
4. Take the user input from user and pass it to the API | 1.6667
5. Retrive the info from API and show it in the display | 1.3333
6. Design the output | 1.5
7. Get the coordinates of the user through google maps | 0.66667
8. Get the coordinates of the restaurents that we receive from API call | 1.5
9. Then pass these info to Google distance matrix API to calculate the expected arrival time by default show walking | 3.3333
10. Display the result on the screen | 0.66667
11. Sort by different filters | 0.66667
Total | 14.8333